## Electricity Bill Generation
EPIC | User Stories
Column1 | As a/an | I want to | So That | Acceptance Criteria | Validation | Task List | Story Point | Actual Time | Start Time | End Time | Task Status | Owner | Comments | Scenario 1 (Pass) | Scenario 2 (Fail)
| Customer | 1.1 Register as customer | I can get authentication permission | Mandatory field must be filled and condition should be fulfilled | Format should be follow as per given | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer (2 hrs) | 1 |  | 2020-05-26 | 2020-05-26 | 1.Done 2. Pending 3. Done 4. Done 5.Done 6.Done | Raj Bhushan |  | Given the customer provides the valid credentials, He will be registered to the portal and will get message registered successfully | Given the customer does not provide the data in proper format , then the customer will not be able to register himself on portal
| Customer | 1.2 View all bill history | I can know how much bill is there for electricity | The customer should be logged in | Proper authorization is required and user should be present in the database. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design(3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer(2 hrs) | 1 |  | 2020-05-27 | pending | 1.Done 2. Pending 3. Done 4. Done 5.Pending 6.Done | Raj Bhushan |  | Given the customer is logged in and now customer can see all the bill which has not been paid | Given the customer has to see his bill history , but if the appropriate bill data is not found for that specific customer , then bill history will not be visible
| Customer | 1.3 Edit the profile | I can update my name , or my email or my phone number | The customer should be logged in | Proper authorization is required and user should be present in the database. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (3 hrs) 4.field validation (30 mins) 5. Develop service layer (1 hr) 6.DAO layer development (30 mins) 7.Controller layer(2 hrs) | 1 |  | 2020-05-29 | 2020-05-29 | 1.Done 2. Pending 3. Done 4. Done 5.Done 6.Done | Raj Bhushan |  | Given the customer is logged in and now customer can update his profile as per choice like customer can update phone number , email Id and name also | Given the customer has to update his profile , but if the appropriate data is not found for that specific customer , then profile cannot be updated
Customer Module | Customer | 1.4 Change the password | I can change my password whenever I want | The customer should be logged in | Proper authorization is required and user should be present in the database. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer (2 hrs) | 1 |  | 2020-06-01 | 2020-06-01 | 1.Done 2. Pending 3. Done 4. Done 5.Done 6.Done | Raj Bhushan |  | Given the customer is logged in and now customer can login into the portal and if wish customer can change their password | Given the customer has to change his password , but if the appropriate data is not found for that specific customer , then password change can be denied
| Customer | 1.5 Send the feedback | I can get better service | The customer should be logged in | Proper authorization is required and user should be present in the database. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer (2 hrs) | 1 |  | 2020-06-08 | 2020-06-08 | 1.Done 2. Pending 3. Done 4. Done 5.Done 6.Done | Raj Bhushan |  | Given the customer has forgotten the password , if he/she gives write customerId , then he /she can reset the password | Given the customer has forgotten the password , and customer has to reset their password ,but if the appropriate data is not found for that specific customer , then resetting of password cannot be execute
| Customer | 1.6View all payment history | I can know how much payment I have paid and how much is pending | The customer should be logged in and there should have been bill generated on him | Proper authorization is required and user should be present in the database. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer (2 hrs) | 1 |  | pending | pending | 1.Done 2. Pending 3. Done 4. Done 5.Done 6.Done | Poonamchand Sahu |  | Given the customer is logged in and now customer can see all the payement which has been done by him | Given the customer has to see his payment history , but if the appropriate payment data is not found for that specific customer , then payment history will not be visible
| Customer | 1.7 Login as customer | I can access the features of portal like viewing bill details, changing password, updating my profile | The customer should be registered | Proper authorization is required and user should be present in the database. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design(3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer(2 hrs) | 1 |  | 2020-05-26 | 2020-05-27 | 1.Done 2. Pending 3. Pending 4. Done 5.Done 6.Done | Poonamchand Sahu |  | Given the customer provides the valid credentials, He will be logged in and redirected to home page. | Given the customer provides the invalid credentials,, He won't be logged in and a pop up will arise stating about the invalid credentials.
| Customer | 1.8 Social media Integration | I can login from social media like google , facebook or twitter | The customer should have been registered | Proper authorization is required and user should be present in the database. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (3 hrs) 4.field validation (30 mins) 5. Develop service layer (1 hr) 6.DAO layer development (30 mins) 7.Controller layer(2 hrs) | 1 |  | 2020-05-28 | pending | 1.Done 2. Pending 3. Pending 4. Done 5.Pending 6.Done 7.Pending | Poonamchand Sahu |  | Given the customer wants to login from social site like facebook or google | Given the customer has to login, but if the credential is wrong then he will not be able to login into portal
| Customer | 1.9 Get detail in PDF format | I can take out the print of all the biil which is pending and also all the payment which has been done by me | The customer should be logged in | Proper authorization is required and user should be present in the database. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer (2 hrs) | 1 |  | 2020-06-01 | 2020-06-01 | 1.Done 2. Pending 3. Pending 4. Done 5.Pending 6.Done | Poonamchand Sahu |  | Given the customer iwant s data in pdf format so that they can keep as evidence | Given the customer wants pdf of bill history and payment history , but if there is no bill or no payement ., then no pdf will generate
| Admin | 1.1 Generate a bill | I can insert the amount generated based on the units with all the details and specifications. | Fields should be of specified format | No field should be null | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer (2 hrs) | 1 |  | 2020-06-02 | 2020-06-02 | 1.Done 2. Pending 3. Done 4. Done 5.Done 6.Done | Midhun Kumar H |  | Given the admin wants to generate a new bill. When the bill is already in the database, then the application will redirect to insert page and display an error message. | Given the admin wants to generate a new bill. But if the bill is already in the database, then the application will redirect to insert page and display an error message.
| Admin | 1.2 Update/Edit the bill | I can update or edit the details and specifications of existing bills. | The fields should be editable and should follow a specified format. | The fields that are updated should be visible in the database. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer (2 hrs) | 1 |  | 2020-06-03 | 2020-06-03 | 1.Done 2. Pending 3. Done 4. Done 5.Done 6.Done | Midhun Kumar H |  | Given the admin has to edit the details of the bill- admin should not be able to edit the bill in any page other than the Edit Page. | Given the admin has to edit the details of the bill- admin should not be able to edit the bill in any page other than the Edit Page.
Bill Module | Admin | 1.3 Delete a bill | He/she can delete a bill when it is redundant or of no use | The fields should be on a specified format and bill must exist. | All fields are required, No field should be null. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer (2 hrs) | 1 |  | 2020-06-02 | 2020-06-02 | 1.Done 2. Pending 3. Done 4. Done 5.Done 6.Done | Midhun Kumar H |  | Given the admin wants to delete a bill. Admin will be able to delete a bill when he will enter a valid and existing bill number. | Given the admin wants to delete a new bill. When admin will enter a invalid bill number he will not be able to delete the bill.
| Admin | 1.4 View the list of all the bills of customers | I can view the list of bills of all existing customers. | Fields should be of specified format and bill must exist. | All fields are required,no field should be null. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design(3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer(2 hrs) | 1 |  | 2020-06-03 | 2020-06-03 | 1.Done 2. Pending 3. Done 4. Done 5.Done 6.Done | Rohit Kumar |  | Given the admin wants to view the list of bills of all existing customers.When he enter valid bill number or customer number he will be able to view the list of bills. | Given the admin wants to view the list of bills of all existing customers.When he enter invalid bill number or customer number he will not be able to view the list of bills.
| Customer | 1.5 View the List of own bills | I can view the list of own previous or current bills. | Fields should be of specified format and bill must exist. | All fields are required,no field should be null. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer (2 hrs) | 1 |  | 2020-06-05 | 2020-06-05 | 1.Done 2. Pending 3. Done 4. Done 5.Done 6.Done | Rohit Kumar |  | Given the customer wants to view the list of his own bills.When he enter valid bill number or customer number he will be able to view the list of bills. | Given the customer wants to view the list of his own bills.When he enter invalid bill number or customer number he will not be able to view the list of bills.
| Admin | 1.1 Fetch Payemnt details | Customer can fetch as the payment details using bill and customer details. | Bill details should be there. | Proper authorization is required and user should be present in the database. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (3 hrs) 4.field validation (30 mins) 5. Develop service layer (1 hr) 6.DAO layer development (30 mins) 7.Controller layer(2 hrs) | 1 |  | 2020-06-07 | 2020-06-07 | 1.Done 2. Pending 3. Done 4. Done 5.Done 6.Done | Rishab Maity |  | Given the customer is logged in and now customer can see all the payement which has been done by him | gIf he/she gives the wrong credebtials he/she cant login to the portal.
Payment Module | Admin | 1.2 Make Payment | Customer can make payment | The customer should be logged in | Proper authorization is required and user should be present in the database. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer (2 hrs) | 1 |  | 2020-06-07 | 2020-06-07 | 1.Done 2. Pending 3. Done 4. Done 5.Done 6.Done | Vikash |  | Customer can make the payment using the bill details. | If he/she gives the wrong bill no he/she cant view his/her bill details.
| Admin | 1.3 Succesful Payement | Customer can see that he/she paid the amount of the bill successfully. | Fields should be of specified format | No field should be null | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer (2 hrs) | 1 |  | 2020-06-08 | 2020-06-08 | 1.Done 2. Pending 3. Done 4. Done 5.Done 6.Done | Rishab Maity |  | After getting all the details he/she can make the payment. | If he/she gives the wrong bill no he/she cant view his/her bill details hence cant make the payment.
| Admin | 1.4 Feedback | Customer can provisde his/her valuable feedback to improve our service. | After completing the payment only he/she can get this feedback form. | optional or he/she can provide valuable comments. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer (2 hrs) | 1 |  | 2020-06-08 | 2020-06-08 | 1.Done 2. Pending 3. Done 4. Done 5.Done 6.Done | Vikash |  | After completing the payment Customer can add his valuable feedback to make our services better. | Customer can also skip this apart as it will be optional.
| Customer | 1.5 Reset the password | I can set the password again | The customer should have valid email Id | Proper authorization is required and user should be present in the database. | 1.Wireframe creation (30 mins) 2. Writing test cases (30 mins) 3. UI design (3 hrs) 4. Develop service layer (1 hr) 5.DAO layer development (1 hr) 6.Controller layer (2 hrs) | 1 |  | 2020-06-08 | 2020-06-08 | 1.Done 2. Pending 3. Done 4. Done 5.Done 6.Done | Poonamchand Sahu |  | Given the customer has forgotten the password , if he/she gives write customerId , then he /she can reset the password | Given the customer has forgotten the password , and customer has to reset their password ,but if the appropriate data is not found for that specific customer , then resetting of password cannot be execute